## Sheet1
USER STORY ID | As a <type of user> | I want to <perform some task> | so that I can <achieve some goal> | Effort | Priority | Value | Complete during this sprint (Y/N)
Sprint 1: 17 April 2019
1 | new user | login to the website | plan a trip | 2.25 | 2.75 | 3 | Y
2 | family member | create a group | my family can plan a trip with me | 2.25 | 2.75 | 2.75
3 | user | see group members in a single list | easily manage a trip | 1 | 2.5 | 2.5
4 | user | view my itinerary items on a map | visually see my trip | 2.25 | 3 | 3
5 | user | add destinations to my trip | plan a trip | 1.5 | 3 | 3
6 | user | rearrange the order of places on my itinerary | refine my trip planning | 1 | 2.25 | 2.75
7 | user | login with my Gmail account | don't need to create a new account | 1.25 | 2 | 2 | Y
8 | group member | view a timeline of the modifications of the trip | see who made the changes and when | 1.75 | 2.25 | 2.25
9 | group member | create a PDF of my trip | take it with me | 1.75 | 1 | 1.75
10 | trip planner | view places of interest in my destination | have ideas about what to do | 2.5 | 1.25 | 2.25
11 | trip planner | be notified when someone makes a change to the trip | am aware of all the changes to the trip | 2 | 1.25 | 2
12 | trip planner | send a group invite to my friends/family | collaborate on trip planning with other users | 2 | 2 | 3
13 | trip planner | be able to generate directions to my destination | plan my routes | 2.75 | 1.5 | 2.25
14 | new user | be instructed as to how to use the website | effectively use the website | 1 | 2.25 | 2.5
15 | user | see what the page is about when I land on it | effectively use the website | 1 | 2.5 | 2.25
16 | trip planner | see options of the methods of travelling between destinations | plan and budget for travel options | 2.25 | 1 | 1.5
17 | user | delete my account when I am done using the service | continue with my life | 2.25 | 1 | 1.75
18 | user | have the option to remember my login details | login without entering my credentials each time | 2 | 2 | 2.25
19 | user | set a profile | other users can identify me | 1.75 | 1.75 | 2.25
20 | website owner | prevent users from uploading pornographic images | protect the website brand | 3 | 1 | 1
21 | user | use local location time on the website | not be confused | 2 | 1.5 | 2
22 | father | receive suggestions of family-friendly destinations | take my family on a holiday | 2.75 | 1.25 | 1.75
23 | user | export a calendar with trip on it | see my trip dates | 2 | 1 | 2.25
24 | user | view a calendar alongside the map | plan the dates of my trip | 2.25 | 1.75 | 2.5
25 | user | receive weather information about the destinations on my map | plan what clothes I am going to pack | 2.5 | 1 | 1.5
26 | user | search for destinations by name | plan my trip | 1.25 | 2.6667 | 3
27 | user | review the places I visited | give feedback to other users | 3 | 1 | 1
28 | user | save and view previous trips | go on the same trip or a modification thereof | 3 | 1 | 3
29 | trip planner | start planning a new trip | plan my trip | 1.75 | 3 | 3
30 | trip planner | plan multiple trips | compartmentalise my personal and work life | 2.25 | 2 | 2.75
31 | trip planner | give my trips titles | compartmentalise my personal and work life | 1 | 2.5 | 3 | Y
32 | business owner | users to agree to terms and conditions when they create an account | be protected legally | 1.25 | 2.5 | 2.25 | Y
33 | user | enter the url | I can see the website | H | M | H | Y
34 | user | want to sign in | to log into my account | M | L | H

## Sheet2
Difficulty |  |  |  |  | Va1ue |  |  |  |  | Priority |  |  |  |  | Sprit 1 (Y/)
2 | 2 | 2 | 3 | 2.25 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2.75 | Y | Y | Y | Y | Y
3 | 2 | 2 | 2 | 2.25 | 3 | 3 | 3 | 2 | 2.75 | 3 | 3 | 3 | 2 | 2.75
1 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 2 | 2.5 | 3 | 3 | 2 | 2 | 2.5
2 | 3 | 2 | 2 | 2.25 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
1 | 1 | 1 | 3 | 1.5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Y | Y | Y | Y
1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 2 | 2.75 | 3 | 3 | 2 | 1 | 2.25 |  | Y
1 | 2 | 1 | 1 | 1.25 | 3 | 2 | 2 | 1 | 2 | 3 | 2 | 2 | 1 | 2 | Y | Y | Y |  | Y
1 | 2 | 2 | 2 | 1.75 | 2 | 2 | 2 | 3 | 2.25 | 1 | 3 | 2 | 3 | 2.25 |  | Y
2 | 2 | 2 | 1 | 1.75 | 1 | 3 | 2 | 1 | 1.75 | 1 | 1 | 1 | 1 | 1
3 | 2 | 3 | 2 | 2.5 | 2 | 3 | 2 | 2 | 2.25 | 1 | 2 | 1 | 1 | 1.25
1 | 2 | 3 | 2 | 2 | 2 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 1 | 1.25
3 | 3 | 2 | 3 | 2.75 | 1 | 3 | 2 | 3 | 2.25 | 1 | 2 | 1 | 2 | 1.5
1 | 1 | 1 | 1 | 1 | 3 | 2 | 3 | 2 | 2.5 | 3 | 3 | 2 | 1 | 2.25 |  | Y
1 | 1 | 1 | 1 | 1 | 3 | 2 | 2 | 2 | 2.25 | 3 | 3 | 2 | 2 | 2.5 | Y | Y
2 | 2 | 2 | 3 | 2.25 | 1 | 1 | 1 | 3 | 1.5 | 1 | 1 | 1 | 1 | 1
1 | 2 | 3 | 3 | 2.25 | 3 | 2 | 1 | 1 | 1.75 | 3 | 2 | 1 | 1 | 1.75 | Y | Y
2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 2.25 | 2 | 2 | 2 | 2 | 2 |  |  |  | Y
1 | 2 | 2 | 2 | 1.75 | 3 | 1 | 2 | 3 | 2.25 | 3 | 1 | 1 | 2 | 1.75 | Y
3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2 | 2 | 3 | 1 | 2 | 2 | 1 | 2 | 3 | 2 | 2 | 1 | 1 | 2 | 1.5
3 | 3 | 3 | 2 | 2.75 | 1 | 2 | 2 | 2 | 1.75 | 1 | 1 | 1 | 2 | 1.25
2 | 2 | 2 | 2 | 2 | 1 | 2 | 3 | 3 | 2.25 | 1 | 1 | 1 | 1 | 1
2 | 3 | 2 | 2 | 2.25 | 1 | 3 | 3 | 3 | 2.5 | 1 | 1 | 2 | 3 | 1.75
2 | 3 | 3 | 2 | 2.5 | 1 | 2 | 1 | 2 | 1.5 | 1 | 1 | 1 | 1 | 1
1 | 2 | 1 | 1 | 1.25 | 3 | 3 | 3 | 3 | 3 | Y | 2 | 3 | 3 | 2.6667 |  | Y | Y
1 | 1 | 3 | 2 | 1.75 | 2 | 2 | 1 | 1 | 1.5 | 2 | 2 | 1 | 2 | 1.75 |  | Y
1 | 1 | 2 | 3 | 1.75 | 3 | 2 | 1 | 2 | 2 | 3 | 2 | 2 | 2 | 2.25 |  | Y
2 | 1 | 1 | 3 | 1.75 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  | Y | Y
2 | 2 | 2 | 3 | 2.25 | 3 | 3 | 3 | 2 | 2.75 | 3 | 3 | 2 | 2 | 2.5 |  | Y
1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 2 | 2.5 |  | Y | Y | Y | Y
1 | 2 | 1 | 1 | 1.25 | 3 | 1 | 3 | 2 | 2.25 | 3 | 3 | 3 | 1 | 2.5 | Y | Y | Y |  | Y